## Sheet2
Blackjack project Tasks | Predicted start date | Actual start date | End date | Total Meeting Minutes | Finished tasks check
Project Presentation project.init() | 2025-01-27 | 2025-01-27 | 2025-02-06 | 60 | TRUE
Project Presentation (Phase 1 Requirements) | 2025-02-27 | 2025-02-27 | 2025-03-06 | 210 | TRUE
Project Presentation (Phase 2 Design) | 2025-03-09 | 2025-03-24 | 2025-04-10 | 455 | TRUE
Project Presentation (Phase 3 Implementation) | 2025-04-11 | 2025-04-16 | 2025-05-06 | 1310 | FALSE
Project Presentation (Phase 3 Testing) | 2025-05-06 |  |  |  | FALSE
Project Presentation (Phase 3 Maintenance)
Meeting Notes | Meeting Days | Time | Minutes
init() Presentation (Discord) | 2025-02-05 | 1:oo ~ 2:00 | 60
GitHub started (in person) | 2025-02-27 | 2:30 ~ 3:10 | 40
SRS Document (in person) | 2025-03-04 | 12:00 ~ 1:05 | 65
SRS Document (Discord) | 2025-03-04 | 6:30 ~ 8:40 | 130
UML Diagrams (Discord) | 2025-03-05 | 12:45 ~ 2:00 PM | 75
Design Phase (inperson) | 2025-03-24 | 2:30 ~3:00 | 30
Design Phase (discord) | 2025-04-06 | 4:30 ~ 7:30 | 170
Design Phase (inperson) | 2025-04-08 | 11:30 ~1:00 | 90
Design Phase (inperson) | 2025-04-08 | 2:15 ~ 3:00 | 45
Design Phase (discord) | 2025-04-09 | 9:30 ~ 11:00 | 90
Design Phase (inperson) | 2025-04-10 | 12:30 ~ 1:00 | 30
Implementation Phase (Discord) | 2025-04-16 | 11:00 ~ 12:00 | 60
Implementation Phase (Discord) | 2025-04-24 | 6:00 ~ 8:00 | 120
Implementation Phase (inperson) | 2025-04-29 | 11:00 ~ 1:00 | 120
Implementation Phase (Discord) | 2025-04-30 | 1:40 ~ 2:30 | 50
Implementation Phase (inperson) | 2025-05-01 | 11:00 ~ 1:00 | 120
Implementation Phase (Discord) | 2025-05-03 | 12:30 ~ 1:30 | 60
Implementation Phase (Discord) | 2025-05-04 | 6:00 ~ 10:00 | 240
Implementation Phase (Discord) | 2025-05-05 | 8:00 ~ 2:00 | 360
Implementation Phase (inperson) | 2025-05-06 | 10:00 ~ 1:00 | 180
Group Name | Requirments phase contribution | Design phase contribution | Implementation phase contribution | Testing phase | Maintainance phase
Mahlet Bekele | Use case | Use case diagram and UI | server (in the start) , player , Penals, testing
Cristian Gonzales | Class UML | client server sequence diagram and use case specification
Armand Tirado | Requirments | General UI and class diagram
Brandon Wall | Requirments | UI, System Architecture and class diagram | Client, Server, Message, GUI, Panels
Kenny Yu | Sequence Diagram | Class diagram and sequence diagram | Client, Server, Message, GUI, Panels